## BUILDUP
| RATE | 350 | 300 | 250 | 225 | 190 | 160 | 110
|  | HOURS | [6 empty] | REIMBURSABLES | FEE | SUMMARY CODE
Comments & Notes | Task | VP | SDR | DR | AD | SC | CM | ACM | LUMP SUM | TOTAL
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs [A]
| Kickoff; review 6-sheet CD Review set and photographs; clarification/RFI list to architect |  |  |  |  | 2 | 2 |  |  | 700 | A
| Masonry takeoff: repointing (bridges, arches, caps, chimneys), brick replacement, stone cap replace/repoint, spall & crack repair, cleaning, sealants, plaques |  |  |  |  | 2 | 10 |  |  | 1980 | A
| Roofing takeoff & pricing: membrane roof replacement at both bridges with flashing and tapered pitch to scuppers; metal roof clean/sealant; rain leaders |  |  |  |  | 3 | 3 |  |  | 1050 | A
| Pricing: masonry restoration unit rates at CT prevailing wage, concrete/handrail/painting items, scaffolding & access, general conditions, GC markups |  |  |  |  | 6 | 3 |  |  | 1620 | A
| Estimate assembly: basis-of-estimate narrative, unforeseen-conditions allowance, contingency, escalation; recommended items as identified lines |  |  |  |  | 3 | 2 |  |  | 890 | A
| Director QA review of draft estimate |  |  | 2 | [5 empty] | 500 | A
| Review call with architect; incorporate comments; final issue |  |  | 1 |  | 2 | 1 |  |  | 790 | A
| Subtotal | 0 | 0 | 3 | 0 | 18 | 21 | 0 |  | 7530 |  | 42 | 179.2857
Optional Site Visit — Storrs, CT [B]
| Site visit to Storrs, CT: field verification of repair extents and access conditions, incl. travel |  |  |  |  | 8 |  |  |  | 1520 | B
| Subtotal | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 1520 |  | 8 | 190
| GRAND TOTAL | 0 | 0 | 3 | 0 | 26 | 21 | 0 |  | 9050

## CLIENT VIEW
ESTIMATING SCOPE OF SERVICES |  |  |  | SUMMARY CODE
Project | Task | Lump Sum Fee | Deliverable
UCONN Holcomb & Whitney Residence Halls — Connector Walkway Repairs | CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | 7530 |  | A
| Optional Site Visit — Storrs, CT | 1520 |  | B
| TOTAL LUMP SUM FEE | 9050
Locked fee model a9a64e82bcc4: total $9,050. If the buildup is edited, re-run `feeprop price` so the proposal and this workbook stay on one number.