## BUILDUP
| RATE | 350 | 300 | 250 | 225 | 190 | 160 | 110
|  | HOURS | [6 empty] | REIMBURSABLES | FEE | SUMMARY CODE
Comments & Notes | Task | VP | SDR | DR | AD | SC | CM | ACM | LUMP SUM | TOTAL
Concept Design Estimate — Interior Renovation [A]
| Kickoff; review concept design package and available existing-conditions documentation |  |  | 2 |  | 2 |  |  |  | 880 | A
| Site walk — Kaufmann Concert Hall, Hall of Mirrors, Weill Art Gallery |  |  | 3 |  | 3 |  |  |  | 1320 | A
| Demolition, architectural finishes, millwork & fixed seating takeoff and pricing |  |  |  |  | 8 | 6 |  |  | 2480 | A
| Theatrical, AV, acoustic & specialty lighting system allowances (with design team input) |  |  |  |  | 4 | 2 |  |  | 1080 | A
| MEP & fire protection modifications within the renovation footprint |  |  |  |  | 6 | 4 |  |  | 1780 | A
| Historic / ornate finish restoration allowances (Hall of Mirrors) |  |  |  |  | 2 | 2 |  |  | 700 | A
| Estimate assembly: GCs, markups, escalation, occupied-venue premiums & logistics |  |  |  |  | 4 | 2 |  |  | 1080 | A
| Principal QA review of draft estimate | 2 |  | 2 | [5 empty] | 1200 | A
| Estimate review meeting, comment incorporation & final issue | 1 |  | 2 |  | 4 | 2 |  |  | 1930 | A
| Subtotal | 3 | 0 | 9 | 0 | 33 | 18 | 0 |  | 12450 |  | 63 | 197.619
| GRAND TOTAL | 3 | 0 | 9 | 0 | 33 | 18 | 0 |  | 12450

## CLIENT VIEW
ESTIMATING SCOPE OF SERVICES |  |  |  | SUMMARY CODE
Project | Task | Lump Sum Fee | Deliverable
92NY — Kaufmann Concert Hall, Hall of Mirrors & Weill Art Gallery Interior Renovation | Concept Design Estimate — Interior Renovation | 12450 |  | A
| TOTAL LUMP SUM FEE | 12450
Locked fee model f6934cc8b273: total $12,450. If the buildup is edited, re-run `feeprop price` so the proposal and this workbook stay on one number.