## Summary
92NY — Kaufmann Concert Hall, Hall of Mirrors & Weill Art Gallery Interior Renovation - Fee Summary
Client: 92NY
Term: 2 months ¦ Escalation: 5%/yr ¦ Lock: f6934cc8b273
Fee by Contract Year
Year 1 | 12450
Subtotal | 12450
TOTAL FEE | 12450
Pricing Discipline
Fee at year-1 rates flat (the trap) | 12450
Escalation capture (margin protected) | 0
Margin by Role
Role | Revenue | Cost | Margin %
Cost Manager | 2880
Director | 2250
Senior Cost Manager | 6270
Vice President | 1050

## Detail
Deliverable | Role | Phase | Cadence | Qty | Hrs each | Total hrs | Base rate | Fee (escalated) | Fee (flat) | Rationale
Concept Design Estimate — Interior Renovation | Director | Estimate Period | once | 1 | 2 | 2 | 250 | 500 | 500 | Kickoff; review concept design package and available existing-conditions documentation
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Kickoff; review concept design package and available existing-conditions documentation
Concept Design Estimate — Interior Renovation | Director | Estimate Period | once | 1 | 3 | 3 | 250 | 750 | 750 | Site walk — Kaufmann Concert Hall, Hall of Mirrors, Weill Art Gallery
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 3 | 3 | 190 | 570 | 570 | Site walk — Kaufmann Concert Hall, Hall of Mirrors, Weill Art Gallery
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 8 | 8 | 190 | 1520 | 1520 | Demolition, architectural finishes, millwork & fixed seating takeoff and pricing
Concept Design Estimate — Interior Renovation | Cost Manager | Estimate Period | once | 1 | 6 | 6 | 160 | 960 | 960 | Demolition, architectural finishes, millwork & fixed seating takeoff and pricing
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Theatrical, AV, acoustic & specialty lighting system allowances (with design team input)
Concept Design Estimate — Interior Renovation | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Theatrical, AV, acoustic & specialty lighting system allowances (with design team input)
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 6 | 6 | 190 | 1140 | 1140 | MEP & fire protection modifications within the renovation footprint
Concept Design Estimate — Interior Renovation | Cost Manager | Estimate Period | once | 1 | 4 | 4 | 160 | 640 | 640 | MEP & fire protection modifications within the renovation footprint
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Historic / ornate finish restoration allowances (Hall of Mirrors)
Concept Design Estimate — Interior Renovation | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Historic / ornate finish restoration allowances (Hall of Mirrors)
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Estimate assembly: GCs, markups, escalation, occupied-venue premiums & logistics
Concept Design Estimate — Interior Renovation | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Estimate assembly: GCs, markups, escalation, occupied-venue premiums & logistics
Concept Design Estimate — Interior Renovation | Vice President | Estimate Period | once | 1 | 2 | 2 | 350 | 700 | 700 | Principal QA review of draft estimate
Concept Design Estimate — Interior Renovation | Director | Estimate Period | once | 1 | 2 | 2 | 250 | 500 | 500 | Principal QA review of draft estimate
Concept Design Estimate — Interior Renovation | Vice President | Estimate Period | once | 1 | 1 | 1 | 350 | 350 | 350 | Estimate review meeting, comment incorporation & final issue
Concept Design Estimate — Interior Renovation | Director | Estimate Period | once | 1 | 2 | 2 | 250 | 500 | 500 | Estimate review meeting, comment incorporation & final issue
Concept Design Estimate — Interior Renovation | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Estimate review meeting, comment incorporation & final issue
Concept Design Estimate — Interior Renovation | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Estimate review meeting, comment incorporation & final issue

## Assumptions
Topic | Assumption | Basis of fee | Why it matters
Concept package contents | The package is assumed to include concept plans and an outline design narrative for each space; design intent not yet drawn will be captured through clearly identified allowances and communicated back for confirmation at the estimate review. | Concept-level estimate in Uniformat on approximately 10,000 SF, allowance-based where the package is not yet developed | What can be measured versus what must be carried as allowance depends on the package's level of development.
Construction budget | The estimate will establish the concept budget from first principles and benchmarks; if a target budget exists, it will be shared at kickoff so variances can be identified. | One baseline concept estimate; no budget-reconciliation exercise assumed | A stated target lets the estimate be presented against the budget with variances identified.
Theatrical, AV and acoustic systems | Theatrical, AV, acoustic, and specialty lighting scope shown in the concept package is carried as identified allowances developed with the design team; vendor-designed systems are priced as allowances only. | Identified allowances per system, based on the package and design team input | These systems can rival the architectural cost of a concert hall renovation and are often owner-procured.
Seating and FF&E | Fixed seating is priced as an allowance if shown in the concept package; loose furniture, fixtures and equipment, and artwork are excluded. | Fixed-seating allowance per the package; loose FF&E and artwork excluded | Seating is a major line in any concert hall renovation; loose FF&E is commonly owner-procured.
Historic and ornate finishes | Restoration scope is priced as identified allowances per the concept package's stated intent; no Landmarks Preservation Commission requirements are assumed unless identified in the package. | Specialty restoration allowances per space; no LPC filings or requirements assumed | Restoration of decorative finishes carries specialty-trade premiums that dwarf standard fit-out rates.
MEP extent | MEP and fire protection work is limited to modifications within the ~10,000 SF renovation footprint; no central plant, service, or riser upgrades are assumed. | MEP modifications within the renovation footprint only | Central plant or infrastructure work would materially change the estimate's scope.
Occupied venue operations and phasing | The building is assumed to remain in operation; an off-hours / occupied-venue work premium and logistics allowance is carried as a percentage on affected trades, with phasing to be developed with the project team. | Percentage premium and logistics allowance on affected trades | Work around an active venue calendar forces off-hours labor and compressed-schedule premiums.
Hazardous materials | An abatement allowance is carried as a separately identified line; hazardous materials survey and abatement design are excluded. | Identified abatement allowance only, quantity unverified | Abatement can materially affect demolition costs in a 1930s building.
Structural and vertical transportation | No structural modifications or vertical transportation work is assumed unless shown in the concept package. | Interior fit-out basis; structure and VT excluded unless drawn | Either would add scope well beyond an interior fit-out basis.
Construction schedule and escalation | The estimate is prepared in current-day dollars with escalation shown as a separately identified line to an assumed construction midpoint approximately 12 months from estimate issue. | Escalation percentage applied as an identified line on the estimate summary | Escalation to the construction midpoint needs a schedule basis.
Estimate schedule | The draft estimate will be issued within two weeks of receipt of a complete concept package, with the final estimate issued within one week of receiving consolidated comments; expedited turnaround can be discussed if required. | Draft in 2 weeks from complete package; final 1 week after comments | The fee assumes a normal working turnaround, not an expedited one.
Review meeting and revisions | One estimate review meeting is included, held virtually; one consolidated round of review comments is incorporated in the final issue. Further meetings, revisions, or re-issues will be billed at the hourly rates herein. | One virtual review meeting and one revision cycle included | Each additional revision cycle adds assembly and review hours.