## BUILDUP
| RATE | 350 | 300 | 250 | 225 | 190 | 160 | 110
|  | HOURS | [6 empty] | REIMBURSABLES | FEE | SUMMARY CODE
Comments & Notes | Task | VP | SDR | DR | AD | SC | CM | ACM | LUMP SUM | TOTAL
Cost Management through 100% Design Development [A]
| Task: Mobilization: cost-control framework, WBS/cost codes by asset-improvement bucket, report formats & procedures; HOURS DR: 8; HOURS SC: 16; HOURS CM: 12 |  | 6960 | A
| Task: Baseline budget establishment & validation across the four asset-improvement buckets; HOURS DR: 8; HOURS SC: 32; HOURS CM: 24 |  | 11920 | A
| Task: Design milestone estimate & contractor pricing reviews (test fit, schematic, 100% DD); HOURS DR: 18; HOURS SC: 72; HOURS CM: 48 |  | 25860 | A
| Task: Design-team & early bid package leveling with recommendation matrices; HOURS SC: 32; HOURS CM: 24 |  | 9920 | A
| Task: Monthly cost report & cost-to-complete forecast (design period); HOURS SC: 50; HOURS CM: 40 |  | 15900 | A
| Task: Commitment & change log maintenance; procurement cost tracking (design period); HOURS SC: 20; HOURS CM: 15 |  | 6200 | A
| Task: Cost oversight & monthly owner cost meeting (design period); HOURS VP: 5; HOURS DR: 15 |  | 5500 | A
| Subtotal | 5 | 0 | 49 | 0 | 222 | 163 | 0 |  | 82260 |  | 439 | 187.3804
Cost Management — Construction through Closeout [B]
| Task: Trade / GMP bid package leveling & recommendation matrices, incl. MWBE participation tracking; HOURS SC: 96; HOURS CM: 72 |  | 29760 | B
| Task: Monthly cost report, cost-to-complete forecast & contingency tracking (four buckets); HOURS SC: 330; HOURS CM: 264 |  | 104940 | B
| Task: Change order review: pricing verification, entitlement, alternatives; change & commitment logs; HOURS SC: 198; HOURS CM: 132 |  | 58740 | B
| Task: Cost oversight & monthly owner cost meeting (construction & closeout); HOURS VP: 33; HOURS DR: 99 |  | 36300 | B
| Task: Final cost reconciliation & closeout cost report per bucket; HOURS DR: 4; HOURS SC: 24; HOURS CM: 16 |  | 8120 | B
| Subtotal | 33 | 0 | 103 | 0 | 648 | 484 | 0 |  | 237860 |  | 1268 | 187.5868
| GRAND TOTAL | 38 | 0 | 152 | 0 | 870 | 647 | 0 |  | 320120

## CLIENT VIEW
ESTIMATING SCOPE OF SERVICES |  |  |  | SUMMARY CODE
Project | Task | Lump Sum Fee | Deliverable
DCAS Fitout, Whitebox & Capital Improvement — 1 Metrotech Center | Cost Management through 100% Design Development | 82260 |  | A
| Cost Management — Construction through Closeout | 237860 |  | B
| Rate escalation across 38-month term (5% at each contract anniversary) | 15462.66 | Hardcoded from fee_model.json lock 3f0585e10b5d: escalated subtotal minus BUILDUP flat rates
| TOTAL LUMP SUM FEE | 335582.66
Locked fee model 3f0585e10b5d: total $335,583. If the buildup is edited, re-run `feeprop price` so the proposal and this workbook stay on one number.