## Summary
DCAS Fitout, Whitebox & Capital Improvement — 1 Metrotech Center - Fee Summary
Client: BGRE
Term: 38 months ¦ Escalation: 5%/yr ¦ Lock: 3f0585e10b5d
Fee by Contract Year
Year 1 | 132715.13
Year 2 | 90819.28
Year 3 | 95360.23
Year 4 | 16688.05
Subtotal | 335582.66
TOTAL FEE | 335582.66
Pricing Discipline
Fee at year-1 rates flat (the trap) | 320120
Escalation capture (margin protected) | 15462.66
Margin by Role
Role | Revenue | Cost | Margin %
Cost Manager | 108554.17
Director | 39673.92
Senior Cost Manager | 173303.73
Vice President | 14050.84

## Detail
Deliverable | Role | Phase | Cadence | Qty | Hrs each | Total hrs | Base rate | Fee (escalated) | Fee (flat) | Rationale
Cost Management through 100% Design Development | Director | Design & Preconstruction | once | 1 | 8 | 8 | 250 | 2000 | 2000 | Mobilization: cost-control framework, WBS/cost codes by asset-improvement bucket, report formats & procedures
Cost Management through 100% Design Development | Senior Cost Manager | Design & Preconstruction | once | 1 | 16 | 16 | 190 | 3040 | 3040 | Mobilization: cost-control framework, WBS/cost codes by asset-improvement bucket, report formats & procedures
Cost Management through 100% Design Development | Cost Manager | Design & Preconstruction | once | 1 | 12 | 12 | 160 | 1920 | 1920 | Mobilization: cost-control framework, WBS/cost codes by asset-improvement bucket, report formats & procedures
Cost Management through 100% Design Development | Director | Design & Preconstruction | once | 1 | 8 | 8 | 250 | 2000 | 2000 | Baseline budget establishment & validation across the four asset-improvement buckets
Cost Management through 100% Design Development | Senior Cost Manager | Design & Preconstruction | once | 1 | 32 | 32 | 190 | 6080 | 6080 | Baseline budget establishment & validation across the four asset-improvement buckets
Cost Management through 100% Design Development | Cost Manager | Design & Preconstruction | once | 1 | 24 | 24 | 160 | 3840 | 3840 | Baseline budget establishment & validation across the four asset-improvement buckets
Cost Management through 100% Design Development | Director | Design & Preconstruction | total | 3 | 6 | 18 | 250 | 4500 | 4500 | Design milestone estimate & contractor pricing reviews (test fit, schematic, 100% DD)
Cost Management through 100% Design Development | Senior Cost Manager | Design & Preconstruction | total | 3 | 24 | 72 | 190 | 13680 | 13680 | Design milestone estimate & contractor pricing reviews (test fit, schematic, 100% DD)
Cost Management through 100% Design Development | Cost Manager | Design & Preconstruction | total | 3 | 16 | 48 | 160 | 7680 | 7680 | Design milestone estimate & contractor pricing reviews (test fit, schematic, 100% DD)
Cost Management through 100% Design Development | Senior Cost Manager | Design & Preconstruction | total | 2 | 16 | 32 | 190 | 6080 | 6080 | Design-team & early bid package leveling with recommendation matrices
Cost Management through 100% Design Development | Cost Manager | Design & Preconstruction | total | 2 | 12 | 24 | 160 | 3840 | 3840 | Design-team & early bid package leveling with recommendation matrices
Cost Management through 100% Design Development | Senior Cost Manager | Design & Preconstruction | monthly | 5 | 10 | 50 | 190 | 9500 | 9500 | Monthly cost report & cost-to-complete forecast (design period)
Cost Management through 100% Design Development | Cost Manager | Design & Preconstruction | monthly | 5 | 8 | 40 | 160 | 6400 | 6400 | Monthly cost report & cost-to-complete forecast (design period)
Cost Management through 100% Design Development | Senior Cost Manager | Design & Preconstruction | monthly | 5 | 4 | 20 | 190 | 3800 | 3800 | Commitment & change log maintenance; procurement cost tracking (design period)
Cost Management through 100% Design Development | Cost Manager | Design & Preconstruction | monthly | 5 | 3 | 15 | 160 | 2400 | 2400 | Commitment & change log maintenance; procurement cost tracking (design period)
Cost Management through 100% Design Development | Director | Design & Preconstruction | monthly | 5 | 3 | 15 | 250 | 3750 | 3750 | Cost oversight & monthly owner cost meeting (design period)
Cost Management through 100% Design Development | Vice President | Design & Preconstruction | monthly | 5 | 1 | 5 | 350 | 1750 | 1750 | Cost oversight & monthly owner cost meeting (design period)
Cost Management — Construction through Closeout | Senior Cost Manager | Construction & Closeout | total | 6 | 16 | 96 | 190 | 19425.74 | 18240 | Trade / GMP bid package leveling & recommendation matrices, incl. MWBE participation tracking
Cost Management — Construction through Closeout | Cost Manager | Construction & Closeout | total | 6 | 12 | 72 | 160 | 12268.87 | 11520 | Trade / GMP bid package leveling & recommendation matrices, incl. MWBE participation tracking
Cost Management — Construction through Closeout | Senior Cost Manager | Construction & Closeout | monthly | 33 | 10 | 330 | 190 | 66775.98 | 62700 | Monthly cost report, cost-to-complete forecast & contingency tracking (four buckets)
Cost Management — Construction through Closeout | Cost Manager | Construction & Closeout | monthly | 33 | 8 | 264 | 160 | 44985.92 | 42240 | Monthly cost report, cost-to-complete forecast & contingency tracking (four buckets)
Cost Management — Construction through Closeout | Senior Cost Manager | Construction & Closeout | monthly | 33 | 6 | 198 | 190 | 40065.58 | 37620 | Change order review: pricing verification, entitlement, alternatives; change & commitment logs
Cost Management — Construction through Closeout | Cost Manager | Construction & Closeout | monthly | 33 | 4 | 132 | 160 | 22492.96 | 21120 | Change order review: pricing verification, entitlement, alternatives; change & commitment logs
Cost Management — Construction through Closeout | Director | Construction & Closeout | monthly | 33 | 3 | 99 | 250 | 26358.94 | 24750 | Cost oversight & monthly owner cost meeting (construction & closeout)
Cost Management — Construction through Closeout | Vice President | Construction & Closeout | monthly | 33 | 1 | 33 | 350 | 12300.84 | 11550 | Cost oversight & monthly owner cost meeting (construction & closeout)
Cost Management — Construction through Closeout | Director | Construction & Closeout | once | 1 | 4 | 4 | 250 | 1064.98 | 1000 | Final cost reconciliation & closeout cost report per bucket
Cost Management — Construction through Closeout | Senior Cost Manager | Construction & Closeout | once | 1 | 24 | 24 | 190 | 4856.43 | 4560 | Final cost reconciliation & closeout cost report per bucket
Cost Management — Construction through Closeout | Cost Manager | Construction & Closeout | once | 1 | 16 | 16 | 160 | 2726.42 | 2560 | Final cost reconciliation & closeout cost report per bucket

## Assumptions
Topic | Assumption | Basis of fee | Why it matters
Scope basis | Our services comprise cost management only (RFP Section 4.4, and the cost functions of Sections 4.5 and 4.8). Project, design, schedule, and risk management, general reporting, commissioning oversight, and tenant relocation coordination are performed by others. | Cost management workstream only; all other owner's-rep functions by others | The fee perimeter must be unambiguous where a broader RFP is answered in part.
Construction value basis | The fee is a level-of-effort lump sum and does not adjust with the construction value; the baseline budget will be established at mobilization from Owner-provided information. | Level-of-effort fee independent of construction value | The fee is built as level of effort, not as a percentage of construction cost.
Term and termination option | The fee is structured in two phases matching the RFP: through 100% Design Development (October 2026 - March 2027) and construction through closeout (March 2027 - December 2029), a 38-month term overall. On termination at 100% DDs, only the first-phase fee applies. | Phase 1 of 5 months; Phase 2 of 33 months; 38-month term | The fee must be severable at the Owner's termination option.
Bucket allocation | For the Owner's cost coding, the fee is allocated 55% to the 100 Gold Tenant Fitout & Demo/LLW, 20% to the Demo/LLW/Whitebox balance, and 25% to Base Building Capital Improvements. Bucket 4 (tenant relocation coordination) is excluded from this cost-management scope. | 55 / 20 / 25 allocation across Buckets 1-3; Bucket 4 excluded | One cost team and one reporting cycle serve all buckets; a per-bucket build-up would double-count effort.
Design milestone reviews | Three milestone estimate and contractor pricing reviews are included through 100% DD (test fit, schematic, and 100% DD issuances). Our scope is review and validation of estimates and pricing; independent detailed milestone estimates can be provided as an additional service. | Three pricing reviews included; independent estimates additional | Each milestone review is a discrete block of senior estimating effort.
Bid packages | Eight bid package levelings are included: two during design/preconstruction (including the design team procurement) and six trade/GMP packages thereafter, each with a leveling sheet and recommendation matrix. Additional packages will be billed at the hourly rates herein. | Eight bid package levelings included | Bid leveling effort scales with the package count.
Change order volume | Change order review is priced as a monthly level-of-effort allowance averaged across the construction period; a sustained surge in change volume materially beyond that allowance will be addressed as an additional service. | Monthly change-review allowance across 33 construction months | Change review is the most volume-sensitive cost-management task.
Meetings and site presence | One monthly owner cost meeting is included throughout the term, at 1 Metrotech Center or virtually; regular site observation is not required for the cost management scope and is not included. | One monthly cost meeting; no routine site observation | Site presence drives senior staff hours.
Reporting and technology | One consolidated monthly cost report covers the buckets with per-bucket breakouts, using our cost management templates and tools, which are included in the fee with full Owner access to the cost data. Integration into an Owner-mandated PMIS can be accommodated and will be scoped at kickoff. | One consolidated monthly cost report with per-bucket breakouts; our tools included | Report multiplicity and platform costs affect effort.
MWBE participation | MWBE participation is tracked within our bid leveling and cost reporting from data provided by bidders and contractors. Formal MWBE compliance monitoring, verification, and certification support are excluded and can be provided as an additional service. | MWBE participation tracking within bid leveling and cost reports | Participation tracking and formal compliance monitoring are different levels of effort.
Rate escalation | Hourly rates escalate 5% at each contract anniversary per our standard terms; the phase fees herein are built on escalated rates by contract year rather than flat year-one rates. | 5% annual rate escalation applied by contract year across the 38-month term | Flat year-one rates across a multi-year term silently give away real cost inflation.
Owner involvement and information access | The Owner will provide timely access to contracts, budgets, invoices, contractor pricing, and pay applications, and decisions within agreed review windows; monthly reports reflect information available at the cutoff date. | Owner-provided data access; monthly reporting cutoff basis | Reporting cadence cannot be met without current commitments and pricing data.
Proposal validity and dates | This proposal is valid for 90 days from submission and assumes a notice to proceed in time for the October 19, 2026 design and construction start; we can mobilize the cost team within two weeks of award. | 90-day validity; mobilization within two weeks of award | Validity and mobilization assumptions hang on the actual award timeline.