## BUILDUP
| RATE | 350 | 300 | 250 | 225 | 190 | 150 | 110
|  | HOURS | [6 empty] | REIMBURSABLES | FEE | SUMMARY CODE
Comments & Notes | Task | VP | SDR | DR | AD | SC | CM | ACM | LUMP SUM | TOTAL
Concept Level Estimate — Energy Conservation Measures [A]
| Kickoff; review ECM scope narrative and FCA recommendations |  |  | 2 |  | 3 |  |  |  | 1070 | A
| Site walk — Synagogue & Community House (one day, incl. travel and field notes) |  |  | 5 |  | 5 |  |  |  | 2200 | A
| Steam-to-hot-water conversion, Option 1: central conversion at Synagogue, street crossing, coil and piping conversion |  |  |  |  | 6 | 4 |  |  | 1740 | A
| Steam-to-hot-water conversion, Option 2: conversion at each building cellar — comparative delta pricing |  |  |  |  | 4 | 2 |  |  | 1060 | A
| Condensate recovery: tanks, pump sets, piping infrastructure, PRV/valve control upgrades, 120F coil resizing at both buildings |  |  |  |  | 5 | 2 |  |  | 1250 | A
| Fan coil / AHU replacement per FCA ((6) perimeter FCUs per floor); three-way to two-way valve conversions |  |  |  |  | 4 | 4 |  |  | 1360 | A
| Ventilation & controls: BMS integration, DCV at Community House, VAV dampers / OA metering at Sanctuary, DOAS heat recovery, off-hours retuning |  |  |  |  | 5 | 3 |  |  | 1400 | A
| Lighting & electrical: LED upgrade per 5th Floor standard; occupancy-based plug-load receptacle controls |  |  |  |  | 1 | 6 |  |  | 1090 | A
| Envelope: Community House window replacement (double-pane IGU base, triple-pane add alternate); wall insulation per-floor basis |  |  |  |  | 2 | 5 |  |  | 1130 | A
| Estimate assembly: markups, GCs, escalation and allowances; Option 1 vs Option 2 comparison summary |  |  |  |  | 5 | 3 |  |  | 1400 | A
| Principal QA review of draft estimate | 2 |  | 3 | [5 empty] | 1450 | A
| Subtotal | 2 | 0 | 10 | 0 | 40 | 29 | 0 |  | 15150 |  | 81 | 187.037
Estimate Review & Final Issue [B]
| Estimate review meeting with Owner and design team (virtual, incl. preparation) | 2 |  | 2 |  | 2 |  |  |  | 1580 | B
| Incorporate one consolidated round of review comments; final issue of concept estimate |  |  |  |  | 3 | 2 |  |  | 870 | B
| Subtotal | 2 | 0 | 2 | 0 | 5 | 2 | 0 |  | 2450 |  | 11 | 222.7273
| GRAND TOTAL | 4 | 0 | 12 | 0 | 45 | 31 | 0 |  | 17600

## CLIENT VIEW
ESTIMATING SCOPE OF SERVICES |  |  |  | SUMMARY CODE
Project | Task | Lump Sum Fee | Deliverable
Synagogue & Community House — Energy Conservation Measures Program | Concept Level Estimate — Energy Conservation Measures | 15150 |  | A
| Estimate Review & Final Issue | 2450 |  | B
| TOTAL LUMP SUM FEE | 17600
Locked fee model 8b8735440843: total $17,600. If the buildup is edited, re-run `feeprop price` so the proposal and this workbook stay on one number.