## Summary
Synagogue & Community House — Energy Conservation Measures Program - Fee Summary
Client: Central Synagogue
Term: 2 months ¦ Escalation: 5%/yr ¦ Lock: 46a87ed1497e
Fee by Contract Year
Year 1 | 18420
Subtotal | 18420
TOTAL FEE | 18420
Pricing Discipline
Fee at year-1 rates flat (the trap) | 18420
Escalation capture (margin protected) | 0
Margin by Role
Role | Revenue | Cost | Margin %
Cost Manager | 5280
Director | 3000
Senior Cost Manager | 8740
Vice President | 1400

## Detail
Deliverable | Role | Phase | Cadence | Qty | Hrs each | Total hrs | Base rate | Fee (escalated) | Fee (flat) | Rationale
Concept Level Estimate — Energy Conservation Measures | Director | Estimate Period | once | 1 | 2 | 2 | 250 | 500 | 500 | Kickoff; review ECM scope narrative and FCA recommendations
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Kickoff; review ECM scope narrative and FCA recommendations
Concept Level Estimate — Energy Conservation Measures | Director | Estimate Period | once | 1 | 4 | 4 | 250 | 1000 | 1000 | Site walk - Synagogue & Community House (one day, incl. travel and field notes)
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Site walk - Synagogue & Community House (one day, incl. travel and field notes)
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 6 | 6 | 190 | 1140 | 1140 | Steam-to-hot-water conversion, Option 1: central conversion at Synagogue, street crossing, coil and piping conversion
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 4 | 4 | 160 | 640 | 640 | Steam-to-hot-water conversion, Option 1: central conversion at Synagogue, street crossing, coil and piping conversion
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Steam-to-hot-water conversion, Option 2: conversion at each building cellar - comparative delta pricing
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Steam-to-hot-water conversion, Option 2: conversion at each building cellar - comparative delta pricing
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Condensate recovery: tanks, pump sets, piping infrastructure, PRV/valve control upgrades, 120F coil resizing at both buildings
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Condensate recovery: tanks, pump sets, piping infrastructure, PRV/valve control upgrades, 120F coil resizing at both buildings
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Fan coil / AHU replacement per FCA ((6) perimeter FCUs per floor); three-way to two-way valve conversions
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 4 | 4 | 160 | 640 | 640 | Fan coil / AHU replacement per FCA ((6) perimeter FCUs per floor); three-way to two-way valve conversions
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 4 | 4 | 190 | 760 | 760 | Ventilation & controls: BMS integration, DCV at Community House, VAV dampers / OA metering at Sanctuary, DOAS heat recovery, off-hours retuning
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 4 | 4 | 160 | 640 | 640 | Ventilation & controls: BMS integration, DCV at Community House, VAV dampers / OA metering at Sanctuary, DOAS heat recovery, off-hours retuning
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Lighting & electrical: LED upgrade per 5th Floor standard; occupancy-based plug-load receptacle controls
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 6 | 6 | 160 | 960 | 960 | Lighting & electrical: LED upgrade per 5th Floor standard; occupancy-based plug-load receptacle controls
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Envelope: Community House window replacement (double-pane IGU base, triple-pane add alternate); wall insulation per-floor basis
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 5 | 5 | 160 | 800 | 800 | Envelope: Community House window replacement (double-pane IGU base, triple-pane add alternate); wall insulation per-floor basis
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 6 | 6 | 190 | 1140 | 1140 | Estimate assembly: markups, GCs, escalation and allowances; Option 1 vs Option 2 comparison summary
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 4 | 4 | 160 | 640 | 640 | Estimate assembly: markups, GCs, escalation and allowances; Option 1 vs Option 2 comparison summary
Concept Level Estimate — Energy Conservation Measures | Vice President | Estimate Period | once | 1 | 2 | 2 | 350 | 700 | 700 | Principal QA review of draft estimate
Concept Level Estimate — Energy Conservation Measures | Director | Estimate Period | once | 1 | 4 | 4 | 250 | 1000 | 1000 | Principal QA review of draft estimate
Concept Level Estimate — Energy Conservation Measures | Vice President | Estimate Period | once | 1 | 2 | 2 | 350 | 700 | 700 | Estimate Review and Final Issue
Concept Level Estimate — Energy Conservation Measures | Director | Estimate Period | once | 1 | 2 | 2 | 250 | 500 | 500 | Estimate Review and Final Issue
Concept Level Estimate — Energy Conservation Measures | Senior Cost Manager | Estimate Period | once | 1 | 6 | 6 | 190 | 1140 | 1140 | Estimate Review and Final Issue
Concept Level Estimate — Energy Conservation Measures | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Estimate Review and Final Issue

## Assumptions
Topic | Assumption | Basis of fee | Why it matters
Design documentation | The estimate will be prepared from the ECM scope narrative, one site walk, and gross-square-foot benchmarks; the FCA report and any available drawings will be made available at kickoff. | Concept (ROM) level estimate in Uniformat, allowance-based quantities on 100,000 GSF total | Concept accuracy and estimating effort both depend on what can be measured versus what must be carried as allowance.
Building areas and floor counts | Building areas and floor counts will be confirmed at the site walk; quantities are pro-rated on 100,000 GSF total pending confirmation. | Per-floor quantities per the scope narrative, e.g. (6) perimeter fan coils per floor at 1 ton / 400 cfm | Per-floor measures (fan coils, VAV dampers, lighting, wall insulation) scale directly with floor count.
Option pricing basis | The base estimate carries Option 2 (conversion at each building), with Option 1 (central conversion with street crossing) priced at concept level and presented as a comparative cost delta. | One base estimate plus one option delta summary | Carrying two full mechanical options materially increases estimating effort.
Street crossing (Option 1) | Street excavation, backfill, pavement restoration, and permitting for Option 1 are carried as an allowance assuming a single trench crossing; no utility relocations are assumed. | Single trench crossing allowance; utility test pits and investigations excluded | Street work is the stated cost driver separating Option 1 from Option 2 and carries high variability.
Lighting upgrade extent | The lighting and plug-load upgrade is priced on the per-floor fixture counts in the scope, applied to all floors not yet renovated to the 5th Floor standard; the floor count will be confirmed at the site walk. | Approximately (30) 2x2 LED and (16) 5-inch recessed LED fixtures per floor, plus occupancy-based receptacle controls | The per-floor fixture counts are given, but the floor count multiplies them.
Occupied operations and phasing | Both buildings are assumed occupied during construction; an off-hours work premium is carried as a percentage allowance on trades working in occupied areas. | Percentage premium allowance on affected mechanical and electrical trades | Off-hours labor premiums materially move mechanical and electrical costs in occupied buildings.
Hazardous materials | An abatement allowance is carried as a separately identified line; hazardous materials survey and abatement design are excluded. | Identified abatement allowance only, quantity unverified | Abatement can swing demolition and piping conversion costs significantly.
Construction schedule and escalation | The estimate is prepared in current-day dollars with escalation shown as a separately identified line to an assumed construction midpoint approximately 18 months from estimate issue. | Escalation percentage applied as an identified line on the estimate summary | Escalation to the construction midpoint is a visible line in any concept estimate and needs a schedule basis.
Review meeting format | One estimate review meeting is included, held virtually; an on-site presentation can be provided as an additional service at the hourly rates herein. | One 2-hour virtual review meeting including preparation | On-site presentation adds travel time for senior staff.
Revision cycles | One consolidated round of review comments is incorporated in the final issue; further revisions or re-issues will be billed at the hourly rates herein. | One revision cycle included | Each additional revision cycle adds assembly and review hours.
Wall insulation extent | Wall insulation is priced on a per-floor unit basis for the same floors assumed for the lighting upgrade, as future-renovation scope. | 2-inch mineral wool at exterior walls including finish removal and replacement, per-floor unit basis | The measure is defined per renovated floor; its quantity is otherwise open-ended.
Window quantities | The window count will be estimated from facade observation at the site walk; the base carries double-pane IGU with the triple-pane unit priced as an add alternate. | Unit cost per window opening, count to be confirmed | Window replacement is priced per unit; the count is the estimate.