## Summary
UCONN Holcomb & Whitney Residence Halls — Connector Walkway Repairs - Fee Summary
Client: Joseph Sepot Architects
Term: 1 months ¦ Escalation: 5%/yr ¦ Lock: 77b64f13667b
Fee by Contract Year
Year 1 | 9050
Subtotal | 9050
TOTAL FEE | 9050
Pricing Discipline
Fee at year-1 rates flat (the trap) | 9050
Escalation capture (margin protected) | 0
Margin by Role
Role | Revenue | Cost | Margin %
Cost Manager | 3360
Director | 750
Senior Cost Manager | 4940

## Detail
Deliverable | Role | Phase | Cadence | Qty | Hrs each | Total hrs | Base rate | Fee (escalated) | Fee (flat) | Rationale
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Kickoff; review 6-sheet CD Review set; clarification/RFI list to architect
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Kickoff; review 6-sheet CD Review set; clarification/RFI list to architect
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Cost Manager | Estimate Period | once | 1 | 10 | 10 | 160 | 1600 | 1600 | Masonry takeoff: repointing (bridges, arches, caps, chimneys), brick replacement, stone cap replace/repoint, spall & crack repair, cleaning, sealants, plaques
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Masonry takeoff: repointing (bridges, arches, caps, chimneys), brick replacement, stone cap replace/repoint, spall & crack repair, cleaning, sealants, plaques
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Senior Cost Manager | Estimate Period | once | 1 | 3 | 3 | 190 | 570 | 570 | Roofing takeoff & pricing: membrane roof replacement at both bridges with flashing and tapered pitch to scuppers; metal roof clean/sealant; rain leaders
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Cost Manager | Estimate Period | once | 1 | 3 | 3 | 160 | 480 | 480 | Roofing takeoff & pricing: membrane roof replacement at both bridges with flashing and tapered pitch to scuppers; metal roof clean/sealant; rain leaders
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Senior Cost Manager | Estimate Period | once | 1 | 6 | 6 | 190 | 1140 | 1140 | Pricing: masonry restoration unit rates at CT prevailing wage, concrete/handrail/painting items, scaffolding & access, general conditions, GC markups
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Cost Manager | Estimate Period | once | 1 | 3 | 3 | 160 | 480 | 480 | Pricing: masonry restoration unit rates at CT prevailing wage, concrete/handrail/painting items, scaffolding & access, general conditions, GC markups
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Senior Cost Manager | Estimate Period | once | 1 | 3 | 3 | 190 | 570 | 570 | Estimate assembly: basis-of-estimate narrative, unforeseen-conditions allowance, contingency, escalation; recommended items as identified lines
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Cost Manager | Estimate Period | once | 1 | 2 | 2 | 160 | 320 | 320 | Estimate assembly: basis-of-estimate narrative, unforeseen-conditions allowance, contingency, escalation; recommended items as identified lines
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Director | Estimate Period | once | 1 | 2 | 2 | 250 | 500 | 500 | Director QA review of draft estimate
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Director | Estimate Period | once | 1 | 1 | 1 | 250 | 250 | 250 | Review call with architect; incorporate comments; final issue
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Senior Cost Manager | Estimate Period | once | 1 | 2 | 2 | 190 | 380 | 380 | Review call with architect; incorporate comments; final issue
CD-Level Cost Estimate — Connector Walkway & Chimney Repairs | Cost Manager | Estimate Period | once | 1 | 1 | 1 | 160 | 160 | 160 | Review call with architect; incorporate comments; final issue
Optional Site Visit — Storrs, CT | Senior Cost Manager | Estimate Period | once | 1 | 8 | 8 | 190 | 1520 | 1520 | Site visit to Storrs, CT: field verification of repair extents and access conditions, incl. travel

## Assumptions
Topic | Assumption | Basis of fee | Why it matters
Documents | The estimate is based solely on the six-sheet CD Review set dated 09/21/26 (CS101, A101, A102, A201, A202, A203); no specifications or photographs have been provided. Repair methods and materials are priced per the keynotes and industry-standard practice for matching existing construction. | 6-sheet CD Review set only; no specifications or photographs | Unit rates for restoration work depend on method (e.g., cutting depth, mortar type, cap material).
Repair quantities | Quantities are measured from the 1/4-inch plans and elevations where dimensioned and otherwise quantified from the keynoted locations and extents on the drawings; unit rates (per SF of repointing, per brick, per LF of cap) are shown so the Owner can adjust quantities if field conditions differ. | Measured quantities with visible unit rates; keynoted extents where undimensioned | Masonry repair quantity is the estimate; it is condition-dependent.
Unforeseen conditions | A separately identified unforeseen-conditions allowance is carried on the masonry and roofing scope in addition to design contingency. | Identified unforeseen-conditions allowance plus design contingency | Restoration projects routinely grow once masonry is opened.
Prevailing wage | All trades are priced at Connecticut prevailing wage rates for the Storrs locality. | CT prevailing wage labor rates | Prevailing wage materially raises labor-intensive restoration rates.
Access and staging | Pipe scaffolding or lifts at both bridges and roof-level staging with slate protection at both chimneys are carried in general conditions; no interior building access is assumed. | Scaffolding/lift and chimney staging allowance in general conditions | Access can equal the repair cost on small masonry jobs.
Occupied campus and schedule | Work is assumed during a campus break or coordinated with Residential Life during normal hours; no premium time is carried unless directed. | Normal working hours; no premium time | Occupied residence halls can force off-hours or summer-only work.
Recommended items | Recommended items are priced as separately identified lines so they can be added to or removed from the base scope. | Recommended items as identified lines | The Owner may elect to include or exclude them.
Roofing system | A fully adhered single-ply or modified bitumen membrane on tapered insulation to achieve pitch to the existing scuppers, with new flashing and counterflashing at the parapets, is assumed; the system will be confirmed with the architect at kickoff. | Membrane on tapered insulation with new flashing; system to be confirmed | Single-ply versus modified bitumen and tapered insulation change the roofing cost materially.
Hazardous materials | An abatement allowance is carried as a separately identified line; survey and abatement design are excluded. | Identified abatement allowance only | Asbestos-containing roofing or caulk changes demolition cost.
Site visit | The base fee is prepared from the drawings only; one site visit to Storrs to field-verify repair extents is offered as an optional add-alternate, priced separately, with mileage billed at cost. | Base from drawings only; site visit optional | Field verification tightens condition-dependent quantities but adds travel.
Review and revisions | One review call with the architect and one consolidated round of comments are included in the final issue; re-pricing of revised or permit-set drawings will be billed at the hourly rates herein. | One review call and one revision cycle | Re-pricing a revised set is additional effort.
Estimate basis and markups | The estimate is in current dollars with escalation to an assumed construction midpoint approximately nine months out shown separately; general conditions, contractor overhead and profit, bonds and insurance, and contingency are shown as separate identified lines; soft costs, design fees, permits, and Owner costs are excluded. | Hard construction cost; markups and escalation as identified lines | The summary must separate construction cost from Owner costs.